## Resourcing
Planning Proposals | [15 empty] | Date: | 2022-06-03
[16 empty] | Manager: |  | [insert name] |  |  | Executive: |  | [insert name]
Projects Summary |  |  |  | 2022 | [11 empty] | 2023 | [11 empty] | 2024
|  |  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Project #1 |  |  | Basic | bar: 2022 Jun to 2023 Jan
Project #2 |  |  | Basic | bar: 2022 Sep to 2023 Apr
Project #3 |  |  | Standard | bar: 2022 Jun to 2023 Jun
Project #4 |  |  | Standard | bar: 2022 Jun to 2023 Jun
Project #5 |  |  | Complex | bar: 2022 Jun to 2023 Nov
Project #6 |  |  | Complex | bar: 2022 Dec to 2024 May
Project #7 |  |  | Principal | bar: 2022 Jun to 2023 Nov
Stage 1 - Pre-Lodgement |  |  |  | 2022 Jun: Stage 4 - Post Gateway
Stage 2 - Planning Proposal |  |  |  | 2022 Jun: Stage 5 - Public Exhibition & Assessment
Stage 3 - Gateway Determination |  |  |  | 2022 Jun: Stage 6 - Finalisation
Planning Resources |  |  |  | 2022 Jan: 2022; 2023 Jan: 2023; 2024 Jan: 2024
|  |  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Internal Resources
Resource 1 | Junior Planner | Project 1 |  | 2022 Jun: 50%; 2022 Jul: 50%; 2022 Aug: 50%; 2022 Sep: 25%; 2022 Oct: 50%; 2022 Nov: 50%; 2022 Dec: 50%; 2023 Jan: 25%
|  | Project 2 |  | 2022 Sep: 50%; 2022 Oct: 50%; 2022 Nov: 50%; 2022 Dec: 25%; 2023 Jan: 50%; 2023 Feb: 50%; 2023 Mar: 75%; 2023 Apr: 25%
Subtotal |  |  |  | 0% | 0% | 0% | 0% | 0% | 50% | 50% | 50% | 75% | 100% | 100% | 75% | 75% | 50% | 75% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Resource 2 | Junior Planner | Project 3 |  | 2022 Jun: 75%; 2022 Jul: 75%; 2022 Aug: 50%; 2022 Sep: 50%; 2022 Oct: 50%; 2022 Nov: 25%; 2022 Dec: 50%; 2023 Jan: 50%; 2023 Feb: 75%; 2023 Mar: 75%; 2023 Apr: 75%; 2023 May: 25%; 2023 Jun: 25%
|  | Project 6 |  | 2022 Dec: 25%; 2023 Jan: 25%; 2023 Feb: 25%; 2023 Mar: 25%; 2023 Apr: 25%; 2023 May: 50%; 2023 Jun: 25%; 2023 Jul: 25%; 2023 Aug: 50%; 2023 Sep: 50%; 2023 Oct: 50%; 2023 Nov: 75%; 2023 Dec: 75%; 2024 Jan: 75%; 2024 Feb: 75%; 2024 Mar: 25%; 2024 Apr: 25%; 2024 May: 25%
|  | Project 7 |  | 2022 Jun: 25%; 2022 Jul: 25%; 2022 Aug: 50%; 2022 Sep: 50%; 2022 Oct: 50%; 2022 Nov: 75%; 2022 Dec: 25%; 2023 Jan: 25%; 2023 Feb: 25%; 2023 Mar: 25%; 2023 Apr: 25%; 2023 May: 25%; 2023 Jun: 50%; 2023 Jul: 75%; 2023 Aug: 50%; 2023 Sep: 50%; 2023 Oct: 50%; 2023 Nov: 25%
Subtotal |  |  |  | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 125% | 125% | 125% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 75% | 75% | 75% | 25% | 25% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Resource 3 | Senior Planner | Project 1 |  | 2022 Jun: 25%; 2022 Jul: 25%; 2022 Aug: 25%; 2022 Sep: 10%; 2022 Oct: 25%; 2022 Nov: 10%; 2022 Dec: 10%; 2023 Jan: 10%
|  | Project 2 |  | 2022 Sep: 25%; 2022 Oct: 25%; 2022 Nov: 25%; 2022 Dec: 25%; 2023 Jan: 25%; 2023 Feb: 10%; 2023 Mar: 10%; 2023 Apr: 10%
|  | Project 3 |  | 2022 Jun: 50%; 2022 Jul: 50%; 2022 Aug: 30%; 2022 Sep: 30%; 2022 Oct: 30%; 2022 Nov: 25%; 2022 Dec: 50%; 2023 Jan: 50%; 2023 Feb: 50%; 2023 Mar: 50%; 2023 Apr: 50%; 2023 May: 75%; 2023 Jun: 75%
Subtotal |  |  |  | 0% | 0% | 0% | 0% | 0% | 75% | 75% | 55% | 65% | 80% | 60% | 85% | 85% | 60% | 60% | 60% | 75% | 75% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Resource 4 | Senior Planner | Project 4 |  | 2022 Jun: 50%; 2022 Jul: 50%; 2022 Aug: 30%; 2022 Sep: 30%; 2022 Oct: 30%; 2022 Nov: 25%; 2022 Dec: 50%; 2023 Jan: 50%; 2023 Feb: 50%; 2023 Mar: 50%; 2023 Apr: 50%; 2023 May: 75%; 2023 Jun: 75%
|  | Project 5 |  | 2022 Jun: 50%; 2022 Jul: 50%; 2022 Aug: 75%; 2022 Sep: 75%; 2022 Oct: 75%; 2022 Nov: 75%; 2022 Dec: 25%; 2023 Jan: 25%; 2023 Feb: 50%; 2023 Mar: 50%; 2023 Apr: 50%; 2023 May: 50%; 2023 Jun: 50%; 2023 Jul: 50%; 2023 Aug: 50%; 2023 Sep: 75%; 2023 Oct: 75%; 2023 Nov: 75%
Subtotal |  |  |  | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 105% | 105% | 105% | 100% | 75% | 75% | 100% | 100% | 100% | 125% | 125% | 50% | 50% | 75% | 75% | 75% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Resource 5 | Director Planning | Project 4 |  | 2022 Jun: 10%; 2022 Jul: 10%; 2022 Aug: 20%; 2022 Sep: 20%; 2022 Oct: 20%; 2022 Nov: 10%; 2022 Dec: 20%; 2023 Jan: 20%; 2023 Feb: 20%; 2023 Mar: 20%; 2023 Apr: 20%; 2023 May: 25%; 2023 Jun: 25%
|  | Project 5 |  | 2022 Jun: 20%; 2022 Jul: 20%; 2022 Aug: 30%; 2022 Sep: 30%; 2022 Oct: 30%; 2022 Nov: 30%; 2022 Dec: 10%; 2023 Jan: 10%; 2023 Feb: 30%; 2023 Mar: 30%; 2023 Apr: 30%; 2023 May: 20%; 2023 Jun: 20%; 2023 Jul: 20%; 2023 Aug: 20%; 2023 Sep: 25%; 2023 Oct: 25%; 2023 Nov: 25%
|  | Project 6 |  | 2022 Dec: 20%; 2023 Jan: 20%; 2023 Feb: 30%; 2023 Mar: 30%; 2023 Apr: 30%; 2023 May: 30%; 2023 Jun: 10%; 2023 Jul: 10%; 2023 Aug: 30%; 2023 Sep: 30%; 2023 Oct: 30%; 2023 Nov: 20%; 2023 Dec: 20%; 2024 Jan: 20%; 2024 Feb: 20%; 2024 Mar: 25%; 2024 Apr: 25%; 2024 May: 25%
|  | Project 7 |  | 2022 Jun: 10%; 2022 Jul: 20%; 2022 Aug: 20%; 2022 Sep: 10%; 2022 Oct: 10%; 2022 Nov: 20%; 2022 Dec: 20%; 2023 Jan: 20%; 2023 Feb: 20%; 2023 Mar: 20%; 2023 Apr: 20%; 2023 May: 20%; 2023 Jun: 20%; 2023 Jul: 20%; 2023 Aug: 15%; 2023 Sep: 15%; 2023 Oct: 15%; 2023 Nov: 15%
Subtotal |  |  |  | 0% | 0% | 0% | 0% | 0% | 40% | 50% | 70% | 60% | 60% | 60% | 70% | 70% | 100% | 100% | 100% | 95% | 75% | 50% | 65% | 70% | 70% | 60% | 20% | 20% | 20% | 25% | 25% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Other Resources |  |  |  | 2022 Jan: 2022; 2023 Jan: 2023; 2024 Jan: 2024
|  |  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Council Resources
Resource 6 | Executive Manager |  |  | 2022 Aug: 1,7; 2022 Oct: 3,4; 2022 Nov: 2,5; 2023 Jan: 1; 2023 Apr: 2; 2023 May: 6; 2023 Jun: 3,4; 2023 Nov: 5,7; 2024 May: 6
Resource 7 | Traffic Lead |  |  | 2022 Jul: 1,7; 2022 Sep: 3,4; 2022 Oct: 1,2,5; 2022 Dec: 3,4; 2023 Jan: 2; 2023 Feb: 5,7; 2023 Mar: 6; 2023 Aug: 6
Resource 8 | Open Space and Recreation |  |  | 2022 Sep: 3,4; 2022 Oct: 1,2,5; 2022 Dec: 3,4; 2023 Feb: 5,7; 2023 Mar: 6; 2023 Aug: 6
Resource 9 | Economics |  |  | 2022 Sep: 3,4; 2022 Oct: 1,2,5; 2022 Dec: 3,4; 2023 Feb: 5,7; 2023 Mar: 6; 2023 Aug: 6
Resource 10 | Civil and Stormwater |  |  | 2022 Jul: 1,7; 2022 Sep: 3,4; 2022 Oct: 1,2,5; 2022 Dec: 3,4; 2023 Feb: 5,7; 2023 Mar: 6; 2023 Aug: 6
External Resources
DPE |  |  |  | 2022 Sep: 1; 2022 Oct: 7; 2022 Nov: 3,4; 2022 Dec: 2; 2023 Jan: 5; 2023 Jul: 6; 2024 Jun: 1; 2024 Jul: 7; 2024 Aug: 3,4; 2024 Sep: 2; 2024 Oct: 5
Transport NSW |  |  |  | 2022 Dec: 1; 2023 Mar: 2; 2023 Apr: 3,4; 2023 Jul: 7; 2023 Aug: 5; 2024 Feb: 6; 2024 Sep: 1; 2024 Dec: 2
RMS |  |  |  | 2022 Dec: 1; 2023 Mar: 2; 2023 Apr: 3,4; 2023 Jul: 7; 2023 Aug: 5; 2024 Feb: 6; 2024 Sep: 1; 2024 Dec: 2
Government Agencies |  |  |  | 2022 Dec: 1; 2023 Mar: 2; 2023 Apr: 3,4; 2023 Jul: 7; 2023 Aug: 5; 2024 Feb: 6; 2024 Sep: 1; 2024 Dec: 2