## Introduction
Intro | Programme Legend
This program is intended to be used if required to aid in the management and tracking of Planning proposal deliverables | Stage
Task
NOTES | Sub Task
Months are broken into 2 week blocks | Milestone | u
Max days noted is as per Planning Guidelines
Durations noted are estimates and must be adjusted by the project officer
Tasks noted are as per planning proposal guidelines
The programe legend is shown to the right, amend colours and add any additional task delineators as required

## Programme
[INSERT PROJECT NAME] Task Name |  |  |  | Duration | Due Date | Responsibility | 2022-01-01 |  | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 |  | 2022-09-01 | 2022-10-01 |  | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 |  | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01
PLANNING PROPOSAL - COMPLEX
Stage 1 -Pre-Lodgement (max. 60 days)
Prepare Scoping Proposal |  |  |  | 4 weeks | 2022-01-28 | Proponent
Submit scoping proposal to Council |  |  |  | Milestone | 2022-01-28 | Proponent |  | u
Review Pre-Lodgement Information |  |  |  | 1 week | 2022-02-04 | Council
Scoping proposal referred to authorities/agencies |  |  |  | 1 week | 2022-02-07 | Council
Pre lodgement meeting |  |  |  | Milestone | 2022-02-09 | Council |  |  | u
Council assessment |  |  |  | 2 weeks | 2022-02-23 | Council
Council provides written feedback to Proponent confirming the points discussed |  |  |  | 1 week | 2022-02-25 | Council
Liaise with Council internal teams to confirm any other matters |  |  |  | 1 week | 2022-03-04 | Council
PP requirements issued |  |  |  | Milestone | 2022-03-04 | Council |  |  |  | u
Stage 2 - Planning Proposal (max. 120 days)
PP Lodgement |  |  |  | Milestone | 2022-06-06 | Proponent | [6 empty] | u
Council assessment |  |  |  | 13 weeks | 2022-08-12 | Council
| Review PP against relevant planning policies |  |  | 1 week
| Referral to relevant Council teams and consolidate comments |  |  | 4 weeks
|  | Engineering |  | 4 weeks
|  | Open Space |  | 4 weeks
|  | Traffic |  | 4 weeks
| Referral to Dept and other statutory authorities and consolidate comments |  |  | 3 weeks
|  | TfNSW |  | 3 weeks
|  | Heritage NSW |  | 3 weeks
|  | SES |  | 3 weeks
| Review PP by General Manager |  |  | 4 weeks
| Request additional information from Proponent and update PP as required |  |  | 4 weeks
| Referral to LPP |  |  | 1 week | [11 empty] | u
Councillor Briefing (if required) |  |  |  | 1 week
Council officers prepare report to Council |  |  |  | 4 weeks
Council decision to support or reject PP |  |  |  | 1 week
Council submits PP to Dept for Gateway |  |  |  | Milestone | [14 empty] | u
Stage 3 - Gateway Determination (max. 45 days)
PP Review |  |  |  | 4 weeks
Recommendation to Minister to Proceed |  |  |  | Milestone | [16 empty] | u
Gateway Determination issued |  |  |  | Milestone | [16 empty] | u
Stage 4 - Post Gateway (max. 70 days)
Council reviews Gateway determination and actions |  |  |  | 1 week
Provide additional info and/or update PP and provide to Dept for review (if required) |  |  |  | 2 weeks
Undertake consultation with authorities and government agencies (if required) |  |  |  | 3 weeks
| TfNSW |  |  | 3 weeks
| Heritage NSW |  |  | 3 weeks
| SES |  |  | 3 weeks
Finalise infrastructure schedules or development contributions plan |  |  |  | 2 weeks
Undertake pre-exhibition adminstrative tasks |  |  |  | 1 week
Stage 5 - Public Exhibition and Assessment (max. 115 days)
Council publicly exhibits PP |  |  |  | 5 weeks
| Advertisements notifying Public Exhibition |  |  | 1 week
| Notification letters with attached fact sheets |  |  | 1 week
| Collateral for Public Exhibition |  |  | 1 week
| Memo to Councillors |  |  | 1 week
| Public Authority Consultation |  |  | 4 weeks
| Public Exhibition Period |  |  | 4 weeks
Review submissions and outline amendments |  |  |  | 4 weeks
| Public Exhibition Summary Report |  |  | 2 weeks
| Responses to Stakeholders |  |  | 2 weeks
Council reviews PP and undertakes changes |  |  |  | 2 weeks
Councillor Briefing (if required) |  |  |  | 1 week
Council officers prepare report for Council Resolution |  |  |  | 2 weeks
Supported PP referred to the Department to finalise the LEP |  |  |  | Milestone | [23 empty] | u
Stage 6 - Finalisation (max. 70 days)
Council resolves to make the LEP as LPMA |  |  |  | Milestone | [24 empty] | u
Prepare drafting instructions for the PCO to draft the LEP |  |  |  | 4 weeks
Council refers mapping to the Department and issues final maps to PCO once endorsed |  |  |  | 4 weeks
Make the LEP and request the Department arrange notification |  |  |  | Milestone | [25 empty] | u
Stage
Task
Sub Task
Milestone |  |  | u
To change task groupings - go to Data Tab > Outline > Group or Ungroup Rows/Columns
Note on A1: Smith, Adam: Tasks are a suggestion based on PP Guidleines, amend as necessary
Note on G1: Smith, Adam: These duration are an estimate, please amend accordinly
Note on I1: Smith, Adam: Insert responsible person / entity here, i.e Coucnil, DPE Consultant