## Intro
Purpose
How This Document Should Be Used
Additional Instructions
PROJECT BUDGET / COST REGISTER
INSTRUCTIONS AND NOTES
This Budget Register is design to support the cost management process for rezoning projects within Council Strategic Planning Teams
This budget register should be used to support rezoning projects identify, manage and monitor project costs.
Each project should customise the budget and consultants required for the specific Planning Proposal.
Add budget items to column F as required. Add appropriate % and associated amount to contingency row as agreed with your manager.
Once a consultant is engaged against a budget line item, add this contract value to column G.
Column J and L will auto populate once values are inserted into columns F and G.
Add invoiced amounts to column N (you will need to insert the cumlative value here of all invoices for that consultant)
Fee remaining will auto populate in column O.
This budget register is structured to be used as a "live" document and updated on a regular basis through the project.
The level of status reporting is subject to the expectation of the business and/or project sponsor (or relevant PMO). Some projects may have other separate reporting requirements.
For enquiries, support, training and general coaching in risk management or project management, please contact:
- Council Finance Team

## Cost Report
PROJECT BUDGET REGISTER: [INSERT PROJECT NAME]
Stage 2: Planning Proposal
Discipline |  | Consultant | (A) | (B) | (C) | (B+C = D) | (A-D=E) | (F) | (E-F = G)
|  |  | Budget | Original Contract Value | Approved Variations | Committed to Date | Variance | Claimed to Date | Fees Remaining
|  |  | ($ ex GST) | ($ ex GST) | ($ ex GST) | ($ ex GST) | ($ ex GST) | ($ ex GST) | ($ ex GST)
Planner |  |  | 50000 | 20000 | 30000 | 50000 | 0 | 10000 | 40000
Economics |  |  | 40000 | 35000 | 0 | 35000 | 5000 | 25000 | 10000
Transport Engineer |  |  | 60000 | 35000 | 25000 | 60000 | 0 | 10000 | 50000
Social Infrastructure |  |  | 20000 | 15000 | 5000 | 20000 | 0 | 15000 | 5000
European and Indigenous Heritage |  |  | 15000 | 15000 | 0 | 15000 | 0 | 15000 | 0
Community Consultation |  |  | 15000 | 15000 | 0 | 15000 | 0 | 15000 | 0
Quantity Surveyor |  |  | 10000 | 8000 | 0 | 8000 | 2000 | 8000 | 0
Contamination and Geotechnical |  |  | 15000 | 15000 | 0 | 15000 | 0 | 15000 | 0
Engineering (civil, services, stormwater) |  |  | 15000 | 15000 | 0 | 15000 | 0 | 15000 | 0
Ecology |  |  | 10000 | 8000 | 0 | 8000 | 2000 | 8000 | 0
add rows above this line if needed
Subtotal (ex GST) |  |  | 250000 | 181000 | 60000 | 241000 | 9000 | 136000 | 105000
Contingency | 15% |  | 37500
SUBTOTAL INCL. CONTINGENCY (ex GST) |  |  | 287500
Stage 3: Gateway Determination
Discipline |  | Consultant | Budget | Original Contract Value | Approved Variations | Committed to Date | Variance | Claimed to Date | Fees Remaining
Urban Design |  |  | 0 | 0 | 0 | 0 | 0 |  | 0
Landscape Architecture |  |  | 0 | 0 | 0 | 0 | 0 |  | 0
Economics |  |  | 0 | 0 | 0 | 0 | 0 |  | 0
Transport Engineer |  |  | 0 | 0 | 0 | 0 | 0 |  | 0
Engineering (civil, services) |  |  | 0 | 0 | 0 | 0 | 0 |  | 0
Engineering (Stormwater) |  |  | 0 | 0 | 0 | 0 | 0 |  | 0
Community Consultation |  |  | 0 | 0 | 0 | 0 | 0 |  | 0
add rows above this line if needed
Subtotal (ex GST) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contingency | 20%
SUBTOTAL INCL. CONTINGENCY (ex GST) |  |  | 0
TOTALS (ex GST) |  |  | 287500 | 181000 | 60000 | 241000 | 9000 | 136000 | 105000
|  | 1330000 |  |  |  |  | 405000 | 405000 | #REF!
|  | 970000 |  |  |  |  | 75000 | 75000 | #REF!
|  | 525000 |  |  |  |  | 75000 | 75000 | #REF!
|  | 80000 |  |  |  |  | 40000 | 40000 | #REF!
|  | 580000 |  |  |  |  | 0 | 0 | #REF!
|  | - |  |  |  |  | 278000 | 278000
|  | 348500 |  |  |  |  | 87300 | 87300 | #REF!
|  | 3833500 |  |  |  |  | 960300 | 960300 | #REF!
Note on C21: Smith, Adam: amend to required %
Note on C35: Smith, Adam: Amend % and formula if required

## Variation Management Checklist
Assessing Variations
Other Details
Refer to contract for maximum timeframes to resolve variations.
Variation Management Checklist
What is the gap between the original scope and variation?
- Encourage external consultants to work within their original contract sum! If you instruct them to do something, ask them whether or not it is a variation.
- Make all decisions based on cost of alternatives – always keep overall budget in mind.
When approving variations, ask:
- What is the change leading to a variation?
- Is the variation essential or required to complete the original scope of works?
- Is the value of the variation reasonable?
- Is the variation calculated correctly? Looking at tasks, time and rates used to calculate the variation. If the contract hourly rates have not been applied – ask the consultant why this is the case.
- Confirm with the consultant whether reductions / savings in the variation are feasible. This is negotiating with the consultant without compromising the quality or timing of the required outcome.

## Invoice Tracker
INVOICE TRACKER |  |  | Last Updated | 2022-10-06
Note | Copy and paste Rows 5-18 as needed for new Consultants. Ensure one row spacing
CONSULTANT
Contract PO |  |  | Original Contract | 60000
Variation 1 (if any)
|  |  | Total | 60000
Claim | Invoice No. | Description | Month | Invoice Amt
1 | 23333 | Initial review of site opps and constraints | 2022-06-01 | 10000
2
3 |  |  |  | $
4 |  |  |  | $
|  |  | Total | 10000
|  |  | Balance Remaining | 50000
CONSULTANT
Contract PO |  |  | Original Contract | $ XX
Variation 1 (if any)
|  |  | Total | 0
Claim | Invoice No. | Description | Month | Invoice Amt
1 |  | i.e. Traffic Modelling 50% | 2022-05-01 | $
2 |  |  | 2022-06-01 | $
3 |  |  |  | $
4 |  |  |  | $
|  |  | Total | 0
|  |  | Balance Remaining | 0
CONSULTANT
Contract PO |  |  | Original Contract | $ XX
Variation 1 (if any)
|  |  | Total | 0
Claim | Invoice No. | Description | Month | Invoice Amt
1 |  | i.e. Traffic Modelling 50% | 2022-05-01 | $
2 |  |  | 2022-06-01 | $
3 |  |  |  | $
4 |  |  |  | $
|  |  | Total | 0
|  |  | Balance Remaining | 0